## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a user, I want to save my progress if I leave the app, so I can multitask while using the application | 2 | Urgent | In Progress | 3
2 | As a user, I want the alarm to vibrate, so I know when to switch activities. | 1 | Urgent | In Progress | 3
3 | As a user, I want the alarm to make a noise, So I know when to switch activities. | 1 | Urgent | In Progress | 3
4 | As a user, I want to send feedback to the developers, so they know how I feel about their app. | 5 | Normal | To Do | 10
5 | As a user, I want to report bugs I find, so they can be fixed quickly and efficiently. | 5 | Normal | To Do | 10
6 | As a user, I want to opt into and out of notifications to use the app, so I can be reminded to use the application. | 3 | High | To Do | 3
7 | As a user, I want to be able to donate to the developers, so I can reward them for creating a helpful application. | 5 | Low | To Do | 5
8 | As a user, I want to choose different Pomodoro intervals, so I can manage my time how I want. | 1 | Urgent | In Progress | 5
9 | As a user, I want to be able to schedule my day, so I spend my time wisely. |  | Normal | To Do | 20
10 | As a user, I want to choose different alarms, so I can personilize it for me. | 3 | High | To Do | 5
11 | As a user, I want different color themes, so I can make it more appealing. | 3 | High | To Do | 3
12 | As a user, I want some motivational quotes, so I can motivate myself. | 4 | Normal | To Do | 5
13 | As a user, I want some motivational media, so I can motivate myself. | 4 | Normal | To Do | 8
14 | As a fitness coach, I want to share custom workouts, so that I can have my trainee follow it when I'm not there. | 4 | Normal | To Do | 20
15 | As a trainee, I want to see my profile's statistics, so that I can see and share how much I have improved over time. | 4 | High | To Do | 10
16 | As a user, I want to have a visible streak on my profile, so that I will be encouraged to not miss a day. | 3 | High | To Do | 5
17 | As a user, I want to favorite my preferred exercises on my profile, so that I can more easily find them later on. | 4 | Urgent | To Do | 8
18 | As a workout buddy, I want to have the option to share on my profile when I've completed my scheduled workout, so that me and my partner can go through this experience together. | 5 | Normal | To Do | 20
19 | As a college student, I want to have access to exercises I can do in my chair, so that I can I can use this app in the library. | 2 | Urgent | In Progress | 8
20 | As a desk-job-worker, I want stretches to be included as available exercises, so that I can keep my back, neck, and shoulders healthy during long days. | 2 | Urgent | In Progress | 8
21 | As a student, I want meditative exercises to be included in the app, so that I can manage my stress while remaining productive. | 4 | Normal | To Do | 20
22 | As a novice to fitness, I want visuals to help guide me during exercises, so that I can use the app without having to stop to research forms. | 3 | High | To Do | 20
23 | As a novice to fitness, I want allow the app to randomly select exercises for me, so that I can see which ones work best for me. | 2 | Urgent | In Progress | 5