## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
12 | As a user, I want some motivational quotes, so I can motivate myself. | 4 | Normal | In Progress | How to implement | Functional KA | 5 | 1 | Everyone - 20% each
13 | As a user, I want some motivational media, so I can motivate myself. | 4 | Normal | In Progress | How to implement | Functional KA | 8 | 1 | Everyone - 20% each
14 | As a fitness coach, I want to share custom workouts, so that I can have my trainee follow it when I'm not there. | 4 | Normal | In Progress | How to implement | Functional KA | 20 | 1 | Everyone - 20% each
15 | As a trainee, I want to see my profile's statistics, so that I can see and share how much I have improved over time. | 4 | High | In Progress | How to implement | Functional KA | 10 | 1 | Everyone - 20% each
17 | As a user, I want to favorite my preferred exercises on my profile, so that I can more easily find them later on. | 4 | Urgent | In Progress | How to implement | Functional KA | 8 | 1 | Everyone - 20% each
21 | As a student, I want meditative exercises to be included in the app, so that I can manage my stress while remaining productive. | 4 | Normal | In Progress | How to implement | Functional KA | 20 | 5 | Everyone - 20% each