## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a user, I want to save my progress if I leave the app, so I can multitask while using the application | 2 | Urgent | In Progress | How to implement | Functional KA | 3 | 1 | Everyone - 20% each
2 | As a desk-job-worker, I want stretches to be included as available exercises, so that I can keep my back, neck, and shoulders healthy during long days. | s | Urgent | In Progress | How to implement | Functional KA | 8 | 1 | Everyone - 20% each
3 | As a novice to fitness, I want allow the app to randomly select exercises for me, so that I can see which ones work best for me. | 2 | Urgent | In Progress | How to implement | Functional KA | 5 | 1 | Everyone - 20% each
4 | As a college student, I want to have access to exercises I can do in my chair, so that I can I can use this app in the library. | 2 | Urgent | In Progress | How to implement | Functional KA | 8 |  | Everyone - 20% each