## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | As a user, I want to opt into and out of notifications to use the app, so I can be reminded to use the application. | 3 |  | In Progress | How to implement | Functional KA | 3 | 1 | Everyone - 20% each
2 | As a user, I want to have a visible streak on my profile, so that I will be encouraged to not miss a day. | 3 |  | In Progress | How to implement | Functional KA | 5 | 1 | Everyone - 20% each
3 | As a user, I want different color themes, so I can make it more appealing. | 3 |  | In Progress | How to implement | Functional KA | 3 | 1 | Everyone - 20% each
4 | As a user, I want to choose different alarms, so I can personalize it for me. | 3 |  | In Progress | How to implement | Functional KA | 5 | 1 | Everyone - 20% each